## Slide 1: Haiti fEMR
Progress, Requirements, and Iteration Plan

## Slide 2: Progress
Finished Iteration 2 and started Iteration 3
Iteration 3 originally was functional navigation bar
Currently:
  Viewable Triage, Medical, Pharmacy page
  Functional Admin page

## Slide 3: Moving To Iteration 3(9/23-9/29)
Goals:
  Kevin: Set up a mock laptop for an Ad-Hoc network, work on (finish?) Triage functionality
  Steve: Finish Navigation, implement Form Validation, and contact a designer, work on (finish?) Medical functionality
  David P: Continue working on the pharmacy page, learn javascript
  David W: Documentation

## Slide 4: Iteration 4 (9/30-10/06)
Goals:
  Have an Ad-Hoc network running
  Completed Pharmacy/Medical/Triage Page
  Completed SQL scripts for database

## Slide 5: Iteration Plan – Feature Overview
Week | Sunday Meeting Milestones - Features | Date
1 | Login Screen | 15-Sep
2 | triage/medical/pharmacy page look and feel | 22-Sep
3 | fully functional site navigation, unit tests, form validation | 29-Sep
4 | fully functional admin section, Ad Hoc Network | 6-Oct
5 | fully functional triage/medical page | 13-Oct
6 | fully functional pharmacy page | 20-Oct
7 | Extras | 27-Oct
8 | Beta Release and Extras | 3-Nov
9 | Extras | 10-Nov
10 | Release Candidate & Extras(?) | 17-Nov
11 | Release | 24-Nov

## Slide 6: Requirements – General
ALL interactions with the patient tracked
  Physician changes vitals? Record old and new
  What nurse did the patient see? What doctor did the patient see? etc
Records are modifiable
Each patient gets a searchable unique ID

## Slide 7: Requirements – Triage /Medical
Vitals:
  Chief complaint
  Blood Pressure
  Heart Rate
  Temperature
  Respirations
  Oxygen
  Height
  Weight
General Info:
  Patient ID
  First Name
  Last Name
  Address
  City
  Age
  Gender
HPI:
  Chief complaint
  Onset
  Severity
  Radiation
  Quality
  Provokes
  Physical Exam
Treatment:
  Assessment
  Problem List
  Prescriptions
  Treatment Given
  Family History

## Slide 8: Requirements - Pharmacy
Read medication prescribed to patients
Prescribe alternate medications (shortages)

## Slide 10: Architecture

## Slide 11: Q&A